## Summary
S258 — COA + GL Finalization Sign-off
Chart of Accounts + General Ledger Finalization for ALL 58 Companies
Bridge Consulting QBO Handoff Package
Companies | Active Accounts | Root Groups Seeded | GL Entries Preserved
58 | 6928 | 290 | 100%
Sprint Metadata
Sprint ID | S258
Sprint Title | COA + GL Finalization for ALL 58 Companies (Bridge QBO Handoff)
Status | COMPLETED
Completed Date | 2026-06-04
Approver | Sam Karazi (CEO)
PR | Bebang-Enterprise-Inc/hrms#770 (MERGED 8b0636f22)
Post-merge fact-check | 35 PASS / 0 FAIL / 0 WARN
Plan reference | docs/plans/2026-06-04-sprint-258-coa-gl-finalization-bridge-handoff.md (v1.2)
Sam Directive Compliance (CEO directive 2026-06-04)
Directive | Live state | Verdict
GLs and COA for all companies ready for Bridge | 58 CSVs in per_company_coa.zip; 6,928 active accounts | YES
Per-store P&L for ALL companies | 49 stores + 4 BEI-TIN stubs each with own Sales tree | YES
BKI P&L = Commissary | BKI populates 4000200 sub-tree only per COA-175-011 | YES
BEI = Head Office P&L (NOT store) | BEI Head Office; 4 stubs are separate Frappe Companies | YES
BFC GO-LIVE structure ready | Fork 1 scaffolding seeded (1104200 + 2104200 + 2102205) | YES
BFI2 → BFT abbr rename (SEC name unchanged) | abbr=BFT; SEC TIN 663-440-106-00000 preserved | YES
Nothing cancelled or deferred | 10 in-session deviations (D0-* + D1-*) all RESOLVED | YES

## Per-Company Counts
# | Company | Abbr | Status (Phase 0) | Total Accounts (Phase 0) | GL Entries (Phase 0) | Parent Company | Is Group | Tax ID
1 | ARANETA GATEWAY - TUNGSTEN CAPITAL HOLDINGS OPC | ARGW | PARTIAL | 114 | 258 | TUNGSTEN CAPITAL HOLDINGS OPC | No | 679-843-234-00000
2 | AYALA EVO CITY - BEBANG MEGA INC. | AYEVO | PARTIAL | 114 | 6 | BEBANG MEGA INC. | No | 010-885-436-00000
3 | AYALA FAIRVIEW TERRACES - BEBANG FT INC. | AFT | PARTIAL | 114 | 8 | BEBANG ENTERPRISE INC. | No | 663-440-106-00000
4 | AYALA MARKET MARKET - BEBANG MARKET MARKET INC. | AMM | PARTIAL | 114 | 68 | BEBANG ENTERPRISE INC. | No | 656-572-595-00000
5 | AYALA SOLENAD - HFFM SOLENAD FOOD SERVICES INC. | AYSOL | PARTIAL | 114 | 72 |  | No | 681-476-808-00000
6 | AYALA UP TOWN CENTER - BEBANG UP TOWN CENTER INC. | UPTC | PARTIAL | 114 | 6 | BEBANG ENTERPRISE INC. | No | 675-270-405-00000
7 | AYALA VERMOSA - BEBANG MEGA INC. | AYVER | HEALTHY | 114 | 22 | BEBANG MEGA INC. | No | 010-885-436-00000
8 | BEBANG ENTERPRISE INC. | BEI | PARTIAL | 331 | 2031 | IRRESISTIBLE INFUSIONS INC. | Yes | 647-243-690-00000
9 | BEBANG FRANCHISE CORP. | BFC | MISSING | 0 | 0 |  | No | 672-618-804-00000
10 | BEBANG FT INC. | BFI2 | MISSING | 0 | 0 | BEBANG ENTERPRISE INC. | Yes | 663-440-106-00000
11 | BEBANG KITCHEN INC. | BKI | PARTIAL | 325 | 13660 | IRRESISTIBLE INFUSIONS INC. | No | 010-880-681-00001
12 | BEBANG MEGA INC. | BMI2 | HEALTHY | 109 | 0 | BEBANG ENTERPRISE INC. | Yes | 010-885-436-00000
13 | BF HOMES - BEBANG BF HOMES INC. | BFH | PARTIAL | 114 | 44 | BEBANG ENTERPRISE INC. | No | 673-762-767-00000
14 | CTTM TOMAS MORATO - B CUBED VENTURES CORP. | CTTM | PARTIAL | 114 | 62 |  | No | 682-574-745-00000
15 | D'VERDE CALAMBA - TAJ FOOD CORP. | DVCAL | PARTIAL | 114 | 38 | TAJ FOOD CORP. | No | 681-325-053-00000
16 | EVER COMMONWEALTH - DLS DESSERT CRAFT INC. | EGC | PARTIAL | 114 | 72 |  | No | 671-219-097-00000
17 | FESTIVAL MALL ALABANG - BEBANG FESTIVAL INC. | FMA | PARTIAL | 114 | 48 | BEBANG ENTERPRISE INC. | No | 672-618-586-00000
18 | IRRESISTIBLE INFUSIONS INC. | III | PARTIAL | 338 | 0 |  | Yes | 634-954-873-00000
19 | LEGACY77 FOOD CORP. | L77 | PARTIAL | 109 | 0 |  | No | 691-654-007-00000
20 | LUCKY CHINATOWN - BEBANG LCT INC. | LCT | PARTIAL | 114 | 72 | BEBANG ENTERPRISE INC. | No | 665-462-689-00000
21 | MEGAWIDE PITX - BEBANG PITX INC. | PTX | PARTIAL | 114 | 40 | BEBANG ENTERPRISE INC. | No | 010-880-712-00000
22 | MEGAWORLD PASEO CENTER - BEBANG PASEO INC. | MPD | PARTIAL | 114 | 72 | BEBANG ENTERPRISE INC. | No | 010-880-720-00000
23 | MEGAWORLD VENICE GRAND CANAL - BEBANG VENICE GRAND CANAL INC. | VGC | PARTIAL | 114 | 72 | BEBANG ENTERPRISE INC. | No | 010-880-690-00000
24 | NAIA T3 - HALO-HALO TERMINAL FOOD CORP. | NAIA | PARTIAL | 114 | 26 |  | No | 690-528-808-00000
25 | ORTIGAS ESTANCIA - BB ESTANCIA FOOD CORP. | ESM | PARTIAL | 114 | 6 |  | No | 693-136-289-00000
26 | ORTIGAS GREENHILLS - BEIFRANCHISE FOOD OPC | GHO | HEALTHY | 87 | 6 |  | No
27 | ROBINSONS ANTIPOLO - BEBANG ENTERPRISE INC. | ROA | MINIMAL | 12 | 8 | BEBANG ENTERPRISE INC. | No | 647-243-690-00000
28 | ROBINSONS GALLERIA SOUTH - TUNGSTEN CAPITAL HOLDINGS OPC | ROBGS | PARTIAL | 114 | 36 | TUNGSTEN CAPITAL HOLDINGS OPC | No
29 | ROBINSONS GENERAL TRIAS - BEBANG MEGA INC. | ROBGT | PARTIAL | 114 | 6 | BEBANG MEGA INC. | No | 010-885-436-00000
30 | ROBINSONS IMUS - BEBANG MEGA INC. | ROBIM | PARTIAL | 114 | 6 | BEBANG MEGA INC. | No | 010-885-436-00000
31 | ROBINSONS PLACE DASMARINAS - FREEZE DELIGHT INC. | ROBDA | PARTIAL | 134 | 12 |  | No | 697-636-476-00000
32 | SM BICUTAN - BEBANG SM BICUTAN INC. | SMBIC | PARTIAL | 114 | 72 | BEBANG ENTERPRISE INC. | No | 010-887-661-00000
33 | SM CALOOCAN - TAJ FOOD CORP. | SMCAL | PARTIAL | 114 | 82 | TAJ FOOD CORP. | No
34 | SM CLARK - RED TALDAWA FOODS OPC | SMCLK | PARTIAL | 114 | 50 |  | No | 687-525-727-00000
35 | SM EAST ORTIGAS - BEBANG SMEO INC. | SMEO | PARTIAL | 114 | 68 | BEBANG ENTERPRISE INC. | No | 665-312-808-00000
36 | SM GRAND CENTRAL - BEBANG GRAND CENTRAL INC. | SMGC | PARTIAL | 114 | 56 | BEBANG ENTERPRISE INC. | No | 010-880-753-00000
37 | SM MALL OF ASIA - BEBANG SMOA INC. | SMMOA | PARTIAL | 114 | 70 | BEBANG ENTERPRISE INC. | No | 665-459-236-00000
38 | SM MANILA - BEBANG ENTERPRISE INC. | SMM | MINIMAL | 12 | 12 | BEBANG ENTERPRISE INC. | No | 647-243-690-00000
39 | SM MARIKINA - BEBANG SM MARIKINA INC. | SMK | HEALTHY | 114 | 70 | BEBANG ENTERPRISE INC. | Yes | 670-282-332-00000
40 | SM MARILAO - BEBANG MARILAO INC. | SMMAR | PARTIAL | 114 | 72 | BEBANG ENTERPRISE INC. | No | 675-267-457-00000
41 | SM MEGAMALL - BEBANG ENTERPRISE INC. | SMMM | MINIMAL | 12 | 0 | BEBANG ENTERPRISE INC. | No | 647-243-690-00000
42 | SM NORTH EDSA - BEBANG NORTH EDSA INC. | SMNE | PARTIAL | 114 | 46 | BEBANG ENTERPRISE INC. | No | 663-447-579-00000
43 | SM PULILAN - BEBANG SMM INC. | SMPUL | PARTIAL | 114 | 40 | BEBANG ENTERPRISE INC. | No | 662-567-267-00000
44 | SM SAN JOSE DEL MONTE - JL TRADE OPC | SJDM | PARTIAL | 114 | 36 |  | No | 775-842-763-00000
45 | SM SANGANDAAN - TUNGSTEN CAPITAL HOLDINGS OPC | SMSDN | PARTIAL | 114 | 64 | TUNGSTEN CAPITAL HOLDINGS OPC | No
46 | SM SOUTHMALL - BEBANG ENTERPRISE INC. | SMS | MINIMAL | 12 | 12 | BEBANG ENTERPRISE INC. | No | 647-243-690-00000
47 | SM STA. ROSA - SWEET HARMONY FOOD CORP. | SMSTR | PARTIAL | 114 | 52 |  | No | 691-378-334-00000
48 | SM TANZA - BEBANG MEGA INC. | SMTZ | PARTIAL | 114 | 46 | BEBANG MEGA INC. | No | 010-885-436-00000
49 | SM TAYTAY - DAY ONES FOOD AND DRINK ESTABLISHMENTS CORP. | SMTAY | PARTIAL | 114 | 30 |  | No | 010-939-944-00000
50 | SM VALENZUELA - BEBANG SMV INC. | SMV | PARTIAL | 114 | 72 | BEBANG ENTERPRISE INC. | No | 665-313-198-00000
51 | STA. LUCIA EAST GRAND MALL - BEBANG SM MARIKINA INC. | SLGM | PARTIAL | 114 | 28 | SM MARIKINA - BEBANG SM MARIKINA INC. | No | 670-282-332-00000
52 | TAJ FOOD CORP. | BDV | HEALTHY | 109 | 0 |  | Yes | 681-325-053-00000
53 | THE GRID ROCKWELL - TASTECARTEL CORP. | TGR | PARTIAL | 114 | 6 |  | No | 672-270-879-00000
54 | THE TERMINAL - BEBANG STARMALL ALABANG INC. | TTA | PARTIAL | 114 | 30 | BEBANG ENTERPRISE INC. | No | 670-277-140-00000
55 | TUNGSTEN CAPITAL HOLDINGS OPC | BAG | HEALTHY | 109 | 0 |  | Yes | 679-843-234-00000
56 | UP TOWN MALL BGC - DMD HOLDINGS INC. | UMBGC | PARTIAL | 114 | 58 |  | No | 649-154-841-00000
57 | VISTA MALL TAGUIG - TRICERN FOOD CORP. | VMTAG | PARTIAL | 114 | 72 |  | No | 010-038-108-00000
58 | XENTROMALL MONTALBAN - PERPETUAL FOOD CORP. | XMM | PARTIAL | 134 | 0 |  | No | 698-838-619-00000
TOTAL

## Frappe→QBO Type Map
Frappe → QuickBooks Online Type Mapping (Plan Appendix F)
Section 1 — Explicit Mappings (18 rules)
Frappe root_type | Frappe account_type | QBO AccountType | QBO DetailType
Asset | Bank | Bank | Checking
Asset | Cash | Bank | CashOnHand
Asset | Receivable | Accounts Receivable | AccountsReceivable
Asset | Stock | Other Current Asset | Inventory
Asset | Fixed Asset | Fixed Asset | MachineryEquipment
Asset | Tax | Other Current Asset | OtherCurrentAssets
Asset | Stock Received But Not Billed | Other Current Liability | OtherCurrentLiabilities
Liability | Payable | Accounts Payable | AccountsPayable
Liability | Tax | Other Current Liability | SalesTaxPayable
Liability | Round Off | Other Current Liability | OtherCurrentLiabilities
Equity | Equity | Equity | OwnersEquity
Income | Income Account | Income | ServiceFeeIncome
Expense | Cost of Goods Sold | Cost of Goods Sold | SuppliesMaterialsCogs
Expense | Expense Account | Expense | OtherBusinessExpenses
Expense | Depreciation | Expense | Depreciation
Expense | Round Off | Expense | OtherMiscellaneousServiceCost
Expense | Tax | Expense | TaxesPaid
Expense | Stock Adjustment | Cost of Goods Sold | SuppliesMaterialsCogs
Section 2 — Root-type Fallback (when account_type unmapped or NULL)
Frappe root_type | Frappe account_type | QBO AccountType | QBO DetailType
Asset | (any unmapped) | Other Current Asset | OtherCurrentAssets
Liability | (any unmapped) | Other Current Liability | OtherCurrentLiabilities
Equity | (any unmapped) | Equity | OwnersEquity
Income | (any unmapped) | Income | OtherPrimaryIncome
Expense | (any unmapped) | Expense | OtherBusinessExpenses
Notes for Bridge during QBO sandbox import
1. DetailType values are QBO Online v3 enumeration; QBO sandbox import will reject any DetailType not in your scope of accounts.
2. Stock Received But Not Billed (SRBNB) maps to Other Current Liability per ERPNext semantics (accrued AP, not Asset) — adjust if your QBO chart uses Asset convention.
3. Inter-Co accounts (DUE FROM / DUE TO) use generic Receivable/Payable — Bridge may want a dedicated DetailType for intercompany.
4. Root group accounts (Asset/Liability/Equity/Income/Expense) inherit root-type fallback — QBO infers grouping from hierarchy, so they may not need explicit AccountType on import.

## 5 Cosmetic Deltas
Known cosmetic deltas (NOT blockers; iterate with Bridge during sandbox import)
# | Delta | Companies affected | Severity | Recommendation
1 | III still carries both old (4000201-206) AND new (4000901-903) discount account_numbers. III has 0 GL postings on either, so this is purely structural noise. | III only | LOW | Bridge can keep both or delete the 4000201-206 on III in sandbox before final import.
2 | BEI `STOCK ADJUSTMENT - BEI` (account_type=Stock) sits under `LOCAL AD & PROMO - BEI` Expense group. Pre-existing orphan; Phase 3c.4 absorbed into mass-normalize and didn't reparent. | BEI only | LOW | Bridge can reparent in QBO post-import. BEI Settings stock_adjustment_account still points correctly; no operational impact.
3 | Some BEI / III accounts retained number prefix in docname (e.g. `4000100 - STORE SALES - BEI`). Phase 5 idempotency check skipped already-UPPER-form accounts before stripping prefix. | BEI ~283 accounts, III ~36 accounts | COSMETIC | QBO uses AccountNumber + AccountName columns separately. Zero impact on QBO import.
4 | BFC Fork 1 scaffolding docnames retain number prefix (`1104200 - DUE FROM BEI - BFC`). Same root cause as #3. | BFC, BEI | COSMETIC | Same as #3 — QBO uses AccountNumber + AccountName, not docname.
5 | QBO DetailType is best-effort for unmapped Frappe account_types (defaults to root_type fallback). | All Companies | KNOWN | QBO sandbox import will surface any rejected DetailType; iterate. Frappe→QBO map (other sheet) handles 18 explicit + 5 root_type fallbacks.

## Validation Checklist
Post-merge fact-check: 35 PASS / 0 FAIL / 0 WARN
# | Assertion | Result
1 | 58 Companies present (expected 58) | PASS
2 | All 58 Companies have all 5 root group accounts (290 total) | PASS
3 | BEBANG FT INC. abbr=BFT (was BFI2) | PASS
4 | BEBANG FT INC. SEC TIN preserved: 663-440-106-00000 | PASS
5 | 0 tabAccount rows ending '- BFI2' | PASS
6 | 0 tabCost Center rows ending '- BFI2' | PASS
7 | ROBINSONS PLACE DASMARINAS - FREEZE DELIGHT INC.: round_off_account = Round Off - ROBDA | PASS
8 | Legacy 2120000 - ROUND OFF - ROBDA disabled=1 | PASS
9 | XENTROMALL MONTALBAN - PERPETUAL FOOD CORP.: round_off_account = Round Off - XMM | PASS
10 | Legacy 2120000 - ROUND OFF - XMM disabled=1 | PASS
11 | BEBANG ENTERPRISE INC.: round_off_account = Round Off - BEI | PASS
12 | JE ACC-JV-2026-00014 docstatus=1 on ROBDA, total_debit=0.8 | PASS
13 | Stock In Hand - III exists | PASS
14 | III default_inventory_account = Stock In Hand - III | PASS
15 | A1: 44 Companies have Stock In Hand - <ABBR> | PASS
16 | L77 stock_received_but_not_billed canonical | PASS
17 | BFC has 26 accounts (expected >= 25) | PASS
18 | BFC Fork 1: 1104200 - DUE FROM BEI - BFC exists | PASS
19 | BFC Fork 1: 2102205 - OUTPUT VAT PAYABLE - BFC exists | PASS
20 | BEI side Fork 1: 2104200 DUE TO BFC - BEI exists | PASS
21 | BFT has 24 accounts (expected >= 19 from Sales tree + 5 roots) | PASS
22 | ROBINSONS ANTIPOLO - BEBANG ENTERPRISE INC.: 36 accounts (>= 24) | PASS
23 | SM MANILA - BEBANG ENTERPRISE INC.: 36 accounts (>= 24) | PASS
24 | SM MEGAMALL - BEBANG ENTERPRISE INC.: 36 accounts (>= 24) | PASS
25 | SM SOUTHMALL - BEBANG ENTERPRISE INC.: 36 accounts (>= 24) | PASS
26 | 0 tabAccount rows with long-form company-name suffix | PASS
27 | Bridge package: per_company_coa.zip present | PASS
28 | Bridge package: coa_export_zip_manifest.csv present | PASS
29 | Bridge package: master_reconciliation.csv present | PASS
30 | Bridge package: validation.md present | PASS
31 | Bridge package: upload_manifest.json present | PASS
32 | Bridge package: SIGNOFF.txt present | PASS
33 | per_company_coa.zip contains 58 CSVs | PASS
34 | Canonical structure verification: ALL CANONICAL (0 violations) | PASS
35 | Total active accounts across 58 Companies: 6928 (Bridge package reported 6928) | PASS